# Project Plan – Brice Aggregates Website Redevelopment (Custom WordPress Theme)

## 1. Project Overview

### Objective

Brice Aggregates ke existing website ko rebuild karna using a fully custom WordPress theme, jisme:

- Better performance & scalability

- Improved UX/UI

- Structured product & services architecture

- Easy-to-manage CMS for the internal team

### Scope

#### In Scope

- Full website redevelopment (existing design retain karte hue)

- Custom WordPress theme development

- Product, Services, News modules (CPT-based)

- Admin panel with role-based access

- Content migration

- Mobile responsiveness

- Basic SEO setup

#### Out of Scope

- E-commerce/booking functionality

- Content writing

- Hosting / domain / third-party costs

- Customer portal

## 2. Project Phases & Timeline

| Phase | Description | Duration |
| --- | --- | --- |
| Discovery & Planning | Requirements, sitemap, wireframes | 3 days |
| UI/UX Design | Page designs + approvals | 4 days |
| Development | Custom theme + backend setup | 7 days |
| Content Migration & QA | Data upload + testing | 2 days |
| Launch | Deployment + UAT | 1 day |

### Total Timeline: ~17 Working Days (3.5 Weeks)

## 3. Work Breakdown Structure (WBS)

### Phase 1 – Discovery & Planning

- Requirement gathering

- Content audit

- Sitemap finalisation

Owner: PM / Business Analyst

### Phase 2 – UI/UX Design

- Homepage design

- Product listing & detail pages

- Services pages

- Mobile responsive layouts

- Design revisions & approval

Owner: UI/UX Designer

### Phase 3 – Development

#### Frontend

- Custom WordPress theme development

- Reusable components (header, footer, CTA, cards)

#### Backend

- Custom Post Types:

  - Products

  - Services

  - News

- Taxonomies & filters

- ACF fields setup

- Admin dashboard

Owner: WordPress Developer

### Phase 4 – Content Migration & QA

- Product data upload

- Services content migration

- News migration

- Cross-device testing

- SEO checklist

Owner: Content Manager + QA

### Phase 5 – Launch

- Final UAT

- DNS go-live

- Performance checks

Owner: PM + Developer

## 4. Deliverables

| Phase | Deliverables |
| --- | --- |
| Discovery | Sitemap, Wireframes |
| Design | Approved UI mockups |
| Development | Fully functional website |
| QA | Tested website (mobile + desktop) |
| Launch | Live website |

## 5. Milestones

| Milestone | Timeline |
| --- | --- |
| Wireframe Approval | End of Week 1 |
| Design Approval | Mid-Week 2 |
| Development Complete | End of Week 3 |
| QA Sign-off | Week 3 |
| Go Live | Week 4 |

## 6. Resource Plan

| Role | Responsibility | Allocation |
| --- | --- | --- |
| Project Manager | Communication & delivery | 15–20% |
| UI/UX Designer | Design & layouts | 20–30% |
| WordPress Developer | Theme & backend | 40–50% |
| QA Engineer | Testing | 15% |
| Content Manager | Data upload | 10–20% |

## 7. Risk & Assumptions

### Risks

- Content delay from the client

- Design approval delays

- Scope creep

- Third-party dependency delays

### Assumptions

- All content & assets the client provides

- Existing design references available

- Timely feedback (24–48 hrs)

- No major change in scope

## 8. Communication Plan

- Weekly progress updates

- Key milestone demos

- Email + Slack communication

- Feedback turnaround: 24–48 hrs

- Single point of contact (PM)

## 9. Success Criteria

The project is marked as successful if:

- Website is fully responsive

- Page load speed optimised

- CMS is easy to manage

- Products & services properly structured

- No critical bugs at launch

- SEO-ready foundation